## PROGRESSION
GELARAN MAJU SDN BHD | [16 empty] | #VALUE!
PROJECT: THE CAPITOL / MSK
Report Date: 29 AUGUST 2026
LEVEL |  | COLD WATER |  |  |  | 44.05% |  |  | SANITARY |  | 33.65% |  |  | IRRIGATION |  | 8%
|  | PIPE SLEEVE | PUMP | PUMP CONTROL PANEL | TRANSFER PUMP PIPES | L31 & 31M ROOF PIPING | CW TENANT | BACKSHAFT CW & FW TOILETS | HOSEREEL FLOORTRAP & STACK | SANITARY TENANT | TOILET PIPE DISTRIBUTION & HACKING | SANITARY TOILETS | SANITARY WARES INSTALLATION | IRRIGATION OUTLET | IRRIGATION INLET | IRRIGATION WIRING | IRRIGATION CONTROL PANEL
13 | TOWER A | 100% | N/A | N/A | 100% | N/A | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 90% | 0% | N/A
14 |  | 100% |  |  | 100% |  | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0%
15 |  | 100% |  |  | 100% |  | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0%
16 |  | 100% |  |  | 100% |  | 90% | 10% | 100% | 100% | 100% | 100% | 50% | 100% | 0% | 0%
17 |  | 100% |  |  | 100% |  | 90% | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 0% | 0%
18 |  | 100% |  |  | 100% |  | 90% | 0% | 100% | 100% | 100% | 100% | 0% | 50% | 0% | 0%
19 |  | 100% |  |  | 100% |  | 90% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0%
20 |  | 100% |  |  | 100% |  | 90% | 0% | 100% | 50% | 0% | 100% | 0% | 0% | 0% | 0%
21 |  | 100% |  |  | 100% |  | 90% | 0% | 10% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
22 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0%
23 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | N/A
24 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
25 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
26 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 80% | 0% | 0% | 0% | 0% | 0%
27 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
28 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
29 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
30 |  | 100% |  |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31 |  | 55% | 90% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31M |  | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13 | TOWER B | 100% | N/A | N/A | 100% | N/A | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 100% | 90% | 0% | N/A
14 |  | 100% |  |  | 100% |  | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0%
15 |  | 100% |  |  | 100% |  | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0%
16 |  | 100% |  |  | 100% |  | 90% | 10% | 100% | 100% | 100% | 100% | 0% | 100% | 0% | 0%
17 |  | 100% |  |  | 100% |  | 90% | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 0% | 0%
18 |  | 100% |  |  | 100% |  | 90% | 0% | 100% | 100% | 100% | 100% | 0% | 50% | 0% | 0%
19 |  | 100% |  |  | 100% |  | 90% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0%
20 |  | 100% |  |  | 100% |  | 90% | 0% | 100% | 50% | 0% | 100% | 0% | 0% | 0% | 0%
21 |  | 100% |  |  | 100% |  | 90% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
22 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0%
23 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | N/A
24 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
25 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
26 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 80% | 0% | 0% | 0% | 0% | 0%
27 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
28 |  | 100% |  |  | 0% |  | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
29 |  | 100% |  |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
30 |  | 100% |  |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31 |  | 50% | 90% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31M |  | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | 93.13% | 45% | 45% | 45% | 0% | 69.75% | 10.5% | 35.5% | 32.5% | 39% | 50% | 11.25% | 27.5% | 4.5% | 0% | 0%

## Sheet1
GELARAN MAJU SDN BHD |  |  |  | #VALUE!
PROJECT: THE CAPITOL / MSK
Report Date: 29 AUGUST 2026
SCOPE |  | TEAM | PROGRESS % | STATUS | SUPAHAM | LEADER | ASSISTANT
COLD WATER | PIPE SLEEVE | suhairi | 93.13% | In Progress | team 1 | SOLIHIN | ASHRAFUL | JIARUL | YASIN
| PUMP | n/a | 45% | In Progress | team 2 | ASGAR | RANA
| PUMP CONTROL PANEL |  | 45% | In Progress | team 3 | SUHAIRI | SUPENDI
| TRANSFER PUMP PIPES | subs-aryan | 45% | In Progress | team 4 | BILAL | FARHAD | SOFIKUL | SYAHIB | AMIRUL | NURUL | NAZMUL
| L31 & 31M ROOF PIPING |  | 0% | Not Started | team 5 | JUWEL | BADOL
| CW TENANT | asgar | 69.75% | In Progress | team 6 | JILLUR | ISLAM
| BACKSHAFT CW & FW TOILETS | jillur/sarip | 10.5% | In Progress | team 7 | SARIP | SYAHIB
SANITARY | HOSEREEL FLOORTRAP & STACK | emon | 35.5% | In Progress | team 8 | EMON | MAHMUD
| SANITARY TENANT |  | 32.5% | In Progress | team 9 | IBNU | DAMIL
| TOILET PIPE DISTRIBUTION & HACKING | bilal | 39% | In Progress | team 10 | KAMAL
| SANITARY TOILETS TOWER A | subs-aipoon | 55% | In Progress
| SANITARY TOILETS TOWER B |  | 45% | In Progress
| SANITARY WARES INSTALLATION | jiarul | 11.25% | In Progress
IRRIGATION | IRRIGATION OUTLET | juwel | 27.5% | In Progress
| IRRIGATION INLET |  | 4.5% | In Progress
| IRRIGATION WIRING |  | 0% | Not Started
| IRRIGATION CONTROL PANEL |  | 0% | Not Started

## Sheet2
GM |  |  | SUBS
1 | SUPAHAM | 2000 | 1 | AIPOON | 0
2 | SOLIHIN | 1000 | 2 | WELDER
3 | ASGAR | 500
4 | SUHAIRI | 700
5 | BILAL | 500
6 | JUWEL | 500
7 | JILLUR | 500
8 | SARIP | 700
9 | EMON | 500
10 | IBNU | 500
11 | KAMAL | 500
12 | YASIN | 500
13 | SOFIKUL | 1000
14 | NAZMUL | 500
15 | MAHMUD | 500
16 | NURUL | 500
17 | JIARUL | n/a
18 | SUPENDI | 500
19 | RANA | 500
20 | ASHRAFUL | 500
21 | FARHAD | 500
22 | BADOL | 500
23 | ISLAM | 500
24 | SYAHIB | 500
25 | AMIRUL | 500
26 | DAMIL | 500
27 | KAMAL | 500
| TOTAL | 15900

## COMPARE
Tower A vs Tower B ¦ % complete
Tower A leads overall by 1.1%
PACKAGE |  | Tower A | Tower B | Gap (A−B) | Leader
COLD WATER |  | 44.39% | 43.71% | 0.6786% | Tower A
SANITARY |  | 34.9% | 32.4% | 2.5% | Tower A
IRRIGATION |  | 8% | 8% | 0% | Tie
OVERALL |  | 32.33% | 31.25% | 1.078% | Tower A
PACKAGE | Item | Tower A | Tower B | Gap (A−B) | Leader
Cold Water | Pipe Sleeve | 93.25% | 93% | 0.25% | Tower A
Cold Water | Pump | 45% | 45% | 0% | Tie
Cold Water | Pump Control Panel | 45% | 45% | 0% | Tie
Cold Water | Transfer Pump Pipes | 45% | 45% | 0% | Tie
Cold Water | L31 & 31M Roof Piping | 0% | 0% | 0% | Tie
Cold Water | CW Tenant | 72% | 67.5% | 4.5% | Tower A
Cold Water | Backshaft CW & FW Toilets | 10.5% | 10.5% | 0% | Tie
Sanitary | Hosereel Floortrap & Stack | 35.5% | 35.5% | 0% | Tie
Sanitary | Sanitary Tenant | 32.5% | 32.5% | 0% | Tie
Sanitary | Toilet Pipe Distribution & Hacking | 39% | 39% | 0% | Tie
Sanitary | Sanitary Toilets | 55% | 45% | 10% | Tower A
Sanitary | Sanitary Wares Installation | 12.5% | 10% | 2.5% | Tower A
Irrigation | Irrigation Outlet | 27.5% | 27.5% | 0% | Tie
Irrigation | Irrigation Inlet | 4.5% | 4.5% | 0% | Tie
Irrigation | Irrigation Wiring | 0% | 0% | 0% | Tie
Irrigation | Irrigation Control Panel | 0% | 0% | 0% | Tie

## FLOORS
Floor-by-floor ¦ % complete
A ahead 6 · B ahead 1 · tie 13
Level | Tower A | Tower B | Gap (A−B) | Leader
13 | 32.5% | 33.33% | -0.8333% | Tower B
14 | 82.5% | 82.5% | 0% | Tie
15 | 82.5% | 82.5% | 0% | Tie
16 | 70.83% | 66.67% | 4.167% | Tower A
17 | 65.83% | 65.83% | 0% | Tie
18 | 61.67% | 61.67% | 0% | Tie
19 | 57.5% | 57.5% | 0% | Tie
20 | 45% | 45% | 0% | Tie
21 | 33.33% | 32.5% | 0.8333% | Tower A
22 | 30% | 30% | 0% | Tie
23 | 15.83% | 15.83% | 0% | Tie
24 | 15.83% | 15.83% | 0% | Tie
25 | 24.17% | 15.83% | 8.333% | Tower A
26 | 22.5% | 22.5% | 0% | Tie
27 | 24.17% | 15.83% | 8.333% | Tower A
28 | 15.83% | 15.83% | 0% | Tie
29 | 15.83% | 8.333% | 7.5% | Tower A
30 | 8.333% | 8.333% | 0% | Tie
31 | 15.67% | 15.33% | 0.3333% | Tower A
31M | 0.625% | 0.625% | 0% | Tie
OVERALL | 36.02% | 34.59% | 1.433% | Tower A

## ORDER
Material Order ¦ qty
Report Date: 29 AUGUST 2026 · Blue = qty/floor and ordered
Package | Material | Unit | Qty / floor | Remaining A | Remaining B | Required | Ordered | Balance | Status | Remarks | Package | Required | Ordered | Balance
Cold Water | Pipe sleeve | nos | 1 | 1.35 | 1.4 | 2.75 | 0 | 2.75 | To Order |  | Cold Water | 81.05 | 0 | 81.05
Cold Water | Transfer pump pipes | floor | 1 | 11 | 11 | 22 | 0 | 22 | To Order |  | Sanitary | 582.3 | 0 | 582.3
Cold Water | CW tenant pipework | floor | 1 | 5.6 | 6.5 | 12.1 | 0 | 12.1 | To Order |  | Irrigation | 111.2 | 0 | 111.2
Cold Water | Backshaft CW & FW pipe | floor | 1 | 17.9 | 17.9 | 35.8 | 0 | 35.8 | To Order |  | TOTAL | 774.55 | 0 | 774.55
Cold Water | L31 & 31M roof piping | lot | 1 | 2 | 2 | 4 | 0 | 4 | To Order
Cold Water | Pump | set | 1 | 1.1 | 1.1 | 2.2 | 0 | 2.2 | To Order
Cold Water | Pump control panel | set | 1 | 1.1 | 1.1 | 2.2 | 0 | 2.2 | To Order
Sanitary | Hosereel set | nos | 6 | 12.9 | 12.9 | 154.8 | 0 | 154.8 | To Order
Sanitary | Floor trap | nos | 6 | 12.9 | 12.9 | 154.8 | 0 | 154.8 | To Order
Sanitary | Sanitary stack pipe | floor | 1 | 12.9 | 12.9 | 25.8 | 0 | 25.8 | To Order
Sanitary | Toilet distribution pipe | floor | 1 | 12.2 | 12.2 | 24.4 | 0 | 24.4 | To Order
Sanitary | Sanitary tenant | floor | 1 | 13.5 | 13.5 | 27 | 0 | 27 | To Order
Sanitary | WC pan | nos | 4 | 9 | 11 | 80 | 0 | 80 | To Order
Sanitary | Wash basin | nos | 4 | 9 | 11 | 80 | 0 | 80 | To Order
Sanitary | Sanitary wares | floor | 1 | 17.5 | 18 | 35.5 | 0 | 35.5 | To Order
Irrigation | Irrigation outlet | nos | 1 | 14.5 | 14.5 | 29 | 0 | 29 | To Order
Irrigation | Irrigation inlet | nos | 1 | 19.1 | 19.1 | 38.2 | 0 | 38.2 | To Order
Irrigation | Irrigation cable | floor | 1 | 20 | 20 | 40 | 0 | 40 | To Order
Irrigation | Irrigation control panel | set | 1 | 2 | 2 | 4 | 0 | 4 | To Order
TOTAL |  |  |  | 195.55 | 201 | 774.55 | 0 | 774.55

## SITE REPORT
Site report ¦ % complete
Report Date: 29 AUGUST 2026
Overall | Cold Water | Sanitary | Irrigation | Men | Day RM
28.57% | 44.05% | 33.65% | 8% | 27 | 15900
Weather | Fair | Shift | Day
Today | Transfer pump + hosereel
Blockers
Tomorrow
Item | Progress | Status | Owner
PIPE SLEEVE | 93.13% | In Progress | suhairi
PUMP | 45% | In Progress | n/a
PUMP CONTROL PANEL | 45% | In Progress | 0
TRANSFER PUMP PIPES | 45% | In Progress | subs-aryan
L31 & 31M ROOF PIPING | 0% | Not Started | 0
CW TENANT | 69.75% | In Progress | asgar
BACKSHAFT CW & FW TOILETS | 10.5% | In Progress | jillur/sarip
HOSEREEL FLOORTRAP & STACK | 35.5% | In Progress | emon
SANITARY TENANT | 32.5% | In Progress | 0
TOILET PIPE DISTRIBUTION & HACKING | 39% | In Progress | bilal
SANITARY TOILETS TOWER A | 55% | In Progress | subs-aipoon
SANITARY TOILETS TOWER B | 45% | In Progress | 0
SANITARY WARES INSTALLATION | 11.25% | In Progress | jiarul
IRRIGATION OUTLET | 27.5% | In Progress | juwel
IRRIGATION INLET | 4.5% | In Progress | 0
IRRIGATION WIRING | 0% | Not Started | 0
IRRIGATION CONTROL PANEL | 0% | Not Started | 0

## PO LOG
PO log ¦ RM
Report Date: 29 AUGUST 2026
Date | PO No | Material | Supplier | Qty | Unit | Amount RM | Status | ETA | Remarks | Still to order | Lines
[10 empty] | To Order | 19
[10 empty] | Partial | 0
[10 empty] | Complete | 0
TOTAL |  |  |  | 0 |  | 0 | 0 POs

## MANPOWER
Manpower vs progress
Report Date: 29 AUGUST 2026
On site | Day RM | Overall | RM / 1% | Package | Progress | Remaining
27 | 15900 | 28.57% | 556.5696 | Cold Water | 44.05% | 55.95%
|  |  |  | Sanitary | 33.65% | 66.35%
Name | Rate RM | On site | Cost today | Irrigation | 8% | 92%
SUPAHAM | 2000 | 1 | 2000
SOLIHIN | 1000 | 1 | 1000
ASGAR | 500 | 1 | 500
SUHAIRI | 700 | 1 | 700
BILAL | 500 | 1 | 500
JUWEL | 500 | 1 | 500
JILLUR | 500 | 1 | 500
SARIP | 700 | 1 | 700
EMON | 500 | 1 | 500
IBNU | 500 | 1 | 500
KAMAL | 500 | 1 | 500
YASIN | 500 | 1 | 500
SOFIKUL | 1000 | 1 | 1000
NAZMUL | 500 | 1 | 500
MAHMUD | 500 | 1 | 500
NURUL | 500 | 1 | 500
JIARUL | n/a | 1 | 0
SUPENDI | 500 | 1 | 500
RANA | 500 | 1 | 500
ASHRAFUL | 500 | 1 | 500
FARHAD | 500 | 1 | 500
BADOL | 500 | 1 | 500
ISLAM | 500 | 1 | 500
SYAHIB | 500 | 1 | 500
AMIRUL | 500 | 1 | 500
DAMIL | 500 | 1 | 500
KAMAL | 500 | 1 | 500
TOTAL |  | 27 | 15900

## AIPOON
AIPOON CLAIM
Report Date: 29 AUGUST 2026
Subcon | AIPOON | Project | THE CAPITOL / MSK | Claim No | AC-001 | Tower | A/B | Prepared | ALVIN | Verified | KHAIRUL
Toilet RM/point | 50 | Tenant RM/point | 30
TOILET L25-31
Level | Basin | Floor trap | Urinal | Stack | RM/toilet | Toilets | RM/level | Progress | Claimed | Paid | Balance
24 | 7 | 16 | 3 | 3 | 1450 | 4 | 5800 | 50% | 2461.5385 | 0 | 2461.5385
25 | 7 | 16 | 3 | 3 | 1450 | 4 | 5800 | 50% | 2461.5385 | 0 | 2461.5385
26 | 7 | 16 | 3 | 3 | 1450 | 4 | 5800 | 0% | 0 | 0 | 0
27 | 7 | 16 | 3 | 3 | 1450 | 4 | 5800 | 100% | 4923.0769 | 0 | 4923.0769
28 | 7 | 16 | 3 | 3 | 1450 | 4 | 5800 | 0% | 0 | 0 | 0
29 | 7 | 16 | 3 | 3 | 1450 | 4 | 5800 | 0% | 0 | 0 | 0
30 | 7 | 16 | 3 | 3 | 1450 | 4 | 5800 | 0% | 0 | 0 | 0
31 | 7 | 16 | 3 | 3 | 1450 | 2 | 2900 | 0% | 0 | 0 | 0
Subtotal | [6 empty] | 37700 |  | 7384.6154 | 0 | 7384.6154
Discount | [6 empty] | -5700
Toilet final | [6 empty] | 32000 |  | 7384.6154 | 0 | 7384.6154
TENANT L25-31
Level | Floor out | Basin out | Hosereel | Stack |  |  | RM/level | Progress | Claimed | Paid | Balance
25 | 12 | 12 | 12 | 12 |  |  | 1440 | 0% | 0 | 0 | 0
26 | 12 | 12 | 12 | 12 |  |  | 1440 | 0% | 0 | 0 | 0
27 | 12 | 12 | 12 | 12 |  |  | 1440 | 100% | 1428.5714 | 0 | 1428.5714
28 | 12 | 12 | 12 | 12 |  |  | 1440 | 0% | 0 | 0 | 0
29 | 12 | 12 | 12 | 12 |  |  | 1440 | 0% | 0 | 0 | 0
30 | 12 | 12 | 12 | 12 |  |  | 1440 | 0% | 0 | 0 | 0
31 | 12 | 12 | 12 | 12 |  |  | 1440 | 0% | 0 | 0 | 0
Subtotal | [6 empty] | 10080 |  | 1428.5714 | 0 | 1428.5714
Discount | [6 empty] | -80
Tenant final | [6 empty] | 10000 |  | 1428.5714 | 0 | 1428.5714
GRAND TOTAL | [6 empty] | 42000 |  | 8813.1868 | 0 | 8813.1868
Per level | [6 empty] | 6000
PHOTO LOG
Level | Toilet photo |  |  |  |  | Tenant photo |  |  |  | Progress | Claimed
24 | #VALUE! | #VALUE! | Paste photo | Paste photo |  | Paste photo | Paste photo | Paste photo | Paste photo | 50% | 0
25 | #VALUE! | #VALUE! | Paste photo | Paste photo |  | Paste photo | Paste photo | Paste photo | Paste photo | 50% | 2461.5385
26 | Paste photo |  | Paste photo | Paste photo |  | Paste photo | Paste photo | Paste photo | Paste photo | 0% | 0
27 | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 100% | 4923.0769
28 | Paste photo | Paste photo | Paste photo | Paste photo |  | Paste photo | Paste photo | Paste photo | Paste photo | 0% | 0
29 | Paste photo | Paste photo | Paste photo | Paste photo |  | Paste photo | Paste photo | Paste photo | Paste photo | 0% | 0
30 | Paste photo | Paste photo | Paste photo | Paste photo |  | Paste photo | Paste photo | Paste photo | Paste photo | 0% | 0
31 | Paste photo | Paste photo | Paste photo | Paste photo |  | Paste photo | Paste photo | Paste photo | Paste photo | 0% | 0
Prepared / date |  |  | Verified by / date |  |  |  | Stamp

## ARIYAN
ARIYAN ¦ SS pipe ¦ RM
Report Date: 29 AUGUST 2026
RM / m | 80 | Fittings extra
TOWER A | [6 empty] | TOWER B (L21-31)
Level | Metres | Labour | Fittings | Fit RM | Line | Status | Level | Metres | Labour | Fittings | Fit RM | Line | Status
13 | 8.6 | 688 | 2 ELBOW | 300 | 988 | DONE | 21 | 4.5 | 360 |  | 0 | 360 | DONE
14 | 4.5 | 360 | 1 ELBOW + 1 CHECK VALVE | 300 | 660 | DONE | 22 | 4.5 | 360 |  | 0 | 360
15 | 4.5 | 360 |  | 0 | 360 | DONE | 23 | 4.5 | 360 |  | 0 | 360
16 | 4.5 | 360 |  | 0 | 360 | DONE | 24 | 4.5 | 360 |  | 0 | 360
17 | 4.5 | 360 |  | 0 | 360 | DONE | 25 | 4.5 | 360 |  | 0 | 360
18 | 4.5 | 360 |  | 0 | 360 | DONE | 26 | 4.5 | 360 |  | 0 | 360
19 | 4.5 | 360 |  | 0 | 360 | DONE | 27 | 5.1 | 408 |  | 0 | 408
20 | 4.5 | 360 |  | 0 | 360 | DONE | 28 | 5.1 | 408 |  | 0 | 408
21 | 4.5 | 360 |  | 0 | 360 | DONE | 29 | 5.1 | 408 |  | 0 | 408
22 | 4.5 | 360 |  | 0 | 360 |  | 30 | 6 | 480 |  | 0 | 480
23 | 4.5 | 360 |  | 0 | 360 |  | 31 | 4.9 | 392 |  | 0 | 392
24 | 4.5 | 360 |  | 0 | 360 |  | TOTAL |  | 4256 |  | 0 | 4256
25 | 4.5 | 360 |  | 0 | 360 |  | Certified DONE |  |  |  |  | 360
26 | 4.5 | 360 |  | 0 | 360
27 | 5.1 | 408 |  | 0 | 408
28 | 5.1 | 408 |  | 0 | 408
29 | 5.1 | 408 |  | 0 | 408
30 | 6 | 480 |  | 0 | 480
31 | 4.9 | 392 |  | 0 | 392
TOTAL |  | 7464 |  | 600 | 8064
Certified DONE |  |  |  |  | 4168